EVENT DAY RUN-SHEET

[Event name] · [Day, DD Month YYYY]

| Venue | [Name] | Address / map link | [ ] |
| --- | --- | --- | --- |
| Event coordinator | [Name] | Coordinator phone | [ ] |
| Backup coordinator | [Name, phone] | Venue manager | [Name, phone] |
| Guests expected | [ ] | Ceremony / muhurat time | [ ] |

Key contacts

| Role | Name | Phone | On site from |
| --- | --- | --- | --- |
| Bride's family point person | [ ] | [ ] | [ ] |
| Groom's family point person | [ ] | [ ] | [ ] |
| Caterer | [ ] | [ ] | [ ] |
| Decorator | [ ] | [ ] | [ ] |
| Photographer / video | [ ] | [ ] | [ ] |
| DJ / sound | [ ] | [ ] | [ ] |
| Makeup artist | [ ] | [ ] | [ ] |
| Priest / officiant | [ ] | [ ] | [ ] |
| Transport | [ ] | [ ] | [ ] |
| Hotel desk | [ ] | [ ] | [ ] |

Vendor arrival and setup

| Time | Vendor | Setup task | Received by |
| --- | --- | --- | --- |
| 06:00 | Decorator | Mandap, stage, entrance, lights | [ ] |
| 09:00 | Tent / sound / generator | Power backup tested, mics checked | [ ] |
| 11:00 | Caterer | Kitchen setup, counters, water station | [ ] |
| 13:00 | Makeup artist | Bridal room ready, lighting, mirror | [ ] |
| 14:00 | Photographer | Getting-ready shots; shot list from the couple | [ ] |
| 16:00 | DJ | Sound check, playlist and do-not-play list | [ ] |

Timeline (sample wedding day: replace with your own)

| Time | Activity | Where | Responsible | Notes |
| --- | --- | --- | --- | --- |
| 06:00 | Venue opens; decoration setup starts | Hall and lawn | Venue manager |  |
| 10:00 | Haldi (if on the same day) | Home / lawn | Bride's family | Old clothes, towels ready |
| 13:00 | Lunch for family and vendors | Dining area | Caterer | Count vendor meals |
| 14:00 | Bride's makeup and hair begins | Bridal room | Makeup artist | 3 to 4 hours |
| 17:30 | Groom gets ready; safa / turban tying | Groom's room | Groom's family |  |
| 18:30 | Baraat gathers; dhol starts | [Meeting point] | Groom's point person | Horse / car ready |
| 19:00 | Baraat procession to the venue | Road to gate | Transport + band | Keep 15 minutes buffer |
| 19:45 | Milni and welcome of the groom's family | Main gate | Bride's family | Garlands, shagun envelopes |
| 20:00 | Jaimala / varmala on stage | Stage | Coordinator | Photographer in position |
| 20:30 | Dinner opens for guests | Dining area | Caterer | Elders served first |
| 21:30 | Family photos on stage | Stage | Photographer | Call families in order of a list |
| 23:00 | Wedding ceremony / pheras (muhurat) | Mandap | Priest | Ritual items checked |
| 01:00 | Ceremony ends; vidaai or send-off | Gate | Both families | Car decorated and fuelled |

Alternative sample: ceremony and reception

| Time | Activity | Responsible |
| --- | --- | --- |
| 15:30 | Guests arrive; ushers seat them | Ushers |
| 16:00 | Ceremony | Officiant |
| 16:45 | Group photos | Photographer |
| 17:00 | Drinks and canapés | Caterer |
| 18:30 | Couple's entrance; dinner served | MC / DJ |
| 19:45 | Speeches and toasts | MC |
| 20:15 | First dance, cake cutting | DJ |
| 20:30 | Dancing | DJ |
| 23:00 | Send-off; venue pack-down | Coordinator |

Emergency kit

Safety pins, needle and thread in outfit colours, fabric tape

Pain relief, antacid, plasters, ORS, any regular medicines of the couple and elders

Phone chargers and power banks, extension cord

Tissues, wet wipes, deodorant, comb, hair pins, spare dupatta or tie

Copies of vendor contracts, run-sheet and the guest list

Cash for tips and small purchases; balance envelopes for vendors (with the coordinator)

Umbrellas and torches; water bottles and dry snacks

Backup plan

| If this happens | We will | Who decides |
| --- | --- | --- |
| Rain or storm | Move to [covered area / hall]; decorator has a rain cover | [ ] |
| Power cut | Generator starts within [ ] minutes; check fuel in the morning | [ ] |
| A vendor is late or does not come | Call the backup contact: [name, phone] | [ ] |
| Baraat or ceremony runs late | Hold dinner / adjust music; tell the caterer and priest | [ ] |
| Someone feels unwell | First aid kit at [place]; nearest hospital: [name, address, phone] | [ ] |
| Ring, documents or envelopes missing | Check with the person holding the day bag: [name] | [ ] |

After the event

Collect gifts, envelopes and the gift register; two people count cash

Pay remaining vendor balances and take receipts

Check the venue for left items; return rented decor and furniture

Hand over the run-sheet notes to whoever settles accounts

Run-sheet version [1] · printed [DD-MM-YYYY] · share the PDF on the family group too.