## How to use
Wedding & Event Planning Checklist (Excel)
Toolkit by GroupChatOn · free template · https://toolkit.groupchaton.com
Type your event date and every task gets a real due date: book the venue a year ahead, send save-the-dates at six months, confirm numbers with the caterer the week before. The list covers Indian wedding customs (muhurat, mehndi, sangeet, haldi, shagun envelopes) and general event planning alike, and you can add or delete tasks freely. Overdue tasks turn red and the Progress sheet shows how much is done in each period.
Colours
Yellow cells: type or pick here.
Grey and white cells: calculate by themselves. Don't type over them.
Steps
1 | On the Settings sheet type the event date and pick the date style.
2 | Read the Checklist sheet once and set the status of tasks that do not apply to Not needed.
3 | Type an owner for each task: who in the family or team will do it.
4 | Add your own tasks in the empty rows at the bottom: pick the period, and the due date fills in.
5 | Update the status as you go; check the overdue (red) tasks every week.
6 | Open the Progress sheet to see how far you are and which period needs attention.
Tips
• | If your event is less than a year away, do the tasks from the earlier periods first: their due dates will already show as overdue.
• | Share the file on OneDrive or Google Drive so each owner updates their own tasks.
• | For a destination wedding, move travel and stay tasks one period earlier: flights and rooms fill up fast.
Full guide, questions and answers, and more free templates:
https://toolkit.groupchaton.com/events/ev-wedding-planning-checklist-excel/
Designed & Developed by: Nivesh Sahayak
Free to use for your own work and your clients' work. Please don't sell or re-publish this file. The calculations are a help, not professional advice: check figures, tax rates and rules before you rely on them.

## Settings
Settings
Yellow cells: type or pick. Everything else in this file follows these settings. |  | Period | Days from event
Event name | Riya & Arjun's Wedding | 12+ months before | -365
Event date | 2027-04-01 | 9-12 months before | -300
Date style | 31-12-2026 | 6-9 months before | -210
|  | 4-6 months before | -150
Currency is shown in headings and totals; you can also type a currency not in the list. Number style changes how big amounts are grouped. Date style changes how every date in this file is shown. |  | 2-3 months before | -75
|  | 1 month before | -30
|  | 2 weeks before | -14
|  | Last week | -5
|  | Day before | -1
|  | On the day | 0
|  | After the event | 14
Days from event: negative = before the event. Change them to move every due date in a period.

## Checklist
Planning checklist
Riya & Arjun's Wedding · event date 01-04-2027
When | Task | Area | Owner | Due date | Status | Days left | Overdue | Notes
12+ months before | Agree the total budget and who pays for which part | Planning | Both families | 2026-04-01 | Done
12+ months before | Fix the date; for a Hindu or Sikh wedding ask the pandit or granthi for muhurat dates first | Rituals | Papa | 2026-04-01 | Done
12+ months before | Make a rough guest count for each function to size the venue | Guests |  | 2026-04-01 | Done
12+ months before | Visit venues: capacity, parking, rooms, kitchen, power backup, rain cover | Venue & vendors | Riya | 2026-04-01 | In progress | -215 | Overdue
12+ months before | Book the venue with a written agreement and cancellation terms | Venue & vendors |  | 2026-04-01 | Done
12+ months before | Decide the functions (roka or engagement, mehndi, sangeet, haldi, wedding, reception) and their dates | Planning |  | 2026-04-01 | To do | -215 | Overdue
12+ months before | Hire a wedding planner or name one family coordinator | Venue & vendors |  | 2026-04-01 | To do | -215 | Overdue
9-12 months before | Book the caterer after a food tasting | Venue & vendors |  | 2026-06-05 | To do | -150 | Overdue
9-12 months before | Book the photographer and videographer (see full albums, not only highlights) | Venue & vendors |  | 2026-06-05 | To do | -150 | Overdue
9-12 months before | Book the decorator and agree on a theme and colours | Venue & vendors |  | 2026-06-05 | To do | -150 | Overdue
9-12 months before | Reserve a block of hotel rooms for guests from out of town | Travel & stay |  | 2026-06-05 | To do | -150 | Overdue
9-12 months before | Start the guest list with phone numbers and addresses | Guests |  | 2026-06-05 | To do | -150 | Overdue
9-12 months before | Make one shared folder for contracts, receipts and lists | Planning |  | 2026-06-05 | To do | -150 | Overdue
6-9 months before | Send save-the-dates to guests who must travel or take leave | Guests |  | 2026-09-03 | To do | -60 | Overdue
6-9 months before | Book the DJ, band, dhol or live musicians | Venue & vendors |  | 2026-09-03 | To do | -60 | Overdue
6-9 months before | Book makeup, hair and mehndi artists after a trial | Attire & beauty |  | 2026-09-03 | To do | -60 | Overdue
6-9 months before | Order the bride's outfits; ask how long alterations take | Attire & beauty |  | 2026-09-03 | To do | -60 | Overdue
6-9 months before | Order jewellery and wedding rings | Attire & beauty |  | 2026-09-03 | To do | -60 | Overdue
6-9 months before | Book the priest, pandit, granthi, officiant or registrar | Rituals |  | 2026-09-03 | To do | -60 | Overdue
6-9 months before | Book a choreographer for sangeet performances (if wanted) | Venue & vendors |  | 2026-09-03 | To do | -60 | Overdue
6-9 months before | Check passports and visas for a destination wedding or the honeymoon | Paperwork |  | 2026-09-03 | To do | -60 | Overdue
4-6 months before | Design and order invitation cards and e-invites | Guests |  | 2026-11-02 | To do | 0
4-6 months before | Plan transport: baraat, guest shuttles, the couple's car | Travel & stay |  | 2026-11-02 | To do | 0
4-6 months before | Order the groom's outfits (sherwani, suit, safa or turban) | Attire & beauty |  | 2026-11-02 | To do | 0
4-6 months before | Book honeymoon travel and stay | Travel & stay |  | 2026-11-02 | To do | 0
4-6 months before | Plan return gifts, favours and welcome bags | Guests |  | 2026-11-02 | To do | 0
4-6 months before | Book tent, furniture, generator and sound if the venue does not provide them | Venue & vendors |  | 2026-11-02 | To do | 0
4-6 months before | Buy or rent outfits for close family | Attire & beauty |  | 2026-11-02 | To do | 0
2-3 months before | Send invitations: cards by hand or post, e-invites by WhatsApp or email | Guests |  | 2027-01-16 | To do | 75
2-3 months before | Finalise the menu for each function, with veg, Jain, vegan and children's options | Venue & vendors |  | 2027-01-16 | To do | 75
2-3 months before | Final fittings of all outfits | Attire & beauty |  | 2027-01-16 | To do | 75
2-3 months before | Get the list of puja and ritual items (samagri) from the priest | Rituals |  | 2027-01-16 | To do | 75
2-3 months before | Plan the sangeet programme and start rehearsals | Planning |  | 2027-01-16 | To do | 75
2-3 months before | Arrange shagun envelopes, trays and items for the rituals | Rituals |  | 2027-01-16 | To do | 75
2-3 months before | Find out the documents needed to register the marriage in your state or country | Paperwork |  | 2027-01-16 | To do | 75
2-3 months before | Book skin and hair treatments for 1 to 2 weeks before | Attire & beauty |  | 2027-01-16 | To do | 75
1 month before | Call or message guests who have not replied | Guests |  | 2027-03-02 | To do | 120
1 month before | Confirm every vendor in writing: date, times, what is included, balance | Venue & vendors |  | 2027-03-02 | To do | 120
1 month before | Make the seating plan and hotel room allocation | Guests |  | 2027-03-02 | To do | 120
1 month before | Write the event-day run-sheet | Planning |  | 2027-03-02 | To do | 120
1 month before | Arrange money for vendor balances and tips in labelled envelopes | Planning |  | 2027-03-02 | To do | 120
1 month before | Plan airport and station pick-ups for guests | Travel & stay |  | 2027-03-02 | To do | 120
2 weeks before | Give the final headcount to the caterer (by the contract deadline) | Venue & vendors |  | 2027-03-18 | To do | 136
2 weeks before | Share the run-sheet with vendors and coordinators | Planning |  | 2027-03-18 | To do | 136
2 weeks before | Send the rooming list to the hotel | Travel & stay |  | 2027-03-18 | To do | 136
2 weeks before | Collect outfits after alterations and try them on | Attire & beauty |  | 2027-03-18 | To do | 136
2 weeks before | Pack the emergency kit (see the run-sheet) | Day-of |  | 2027-03-18 | To do | 136
2 weeks before | Give the DJ the song list and a do-not-play list | Venue & vendors |  | 2027-03-18 | To do | 136
Last week | Walk through the venue with the decorator and venue manager | Venue & vendors |  | 2027-03-27 | To do | 145
Last week | Pack a bag for each function for the couple | Attire & beauty |  | 2027-03-27 | To do | 145
Last week | Hand vendor balance envelopes to the coordinator | Planning |  | 2027-03-27 | To do | 145
Last week | Confirm arrival times with every vendor | Venue & vendors |  | 2027-03-27 | To do | 145
Last week | Name family members to welcome guests and to receive gifts | Guests |  | 2027-03-27 | To do | 145
Last week | Mehndi and haldi arrangements ready (if held this week) | Rituals |  | 2027-03-27 | To do | 145
Day before | Check all ritual items against the priest's list | Rituals |  | 2027-03-31 | To do | 149
Day before | Charge phones, power banks and camera batteries | Day-of |  | 2027-03-31 | To do | 149
Day before | Keep IDs, rings, documents and shagun envelopes in one bag with a trusted person | Day-of |  | 2027-03-31 | To do | 149
Day before | Eat well and sleep early | Day-of |  | 2027-03-31 | To do | 149
On the day | Coordinator follows the run-sheet; the couple stays off the phone | Day-of |  | 2027-04-01 | To do | 150
On the day | Receive vendors and check setup against the plan | Day-of |  | 2027-04-01 | To do | 150
On the day | One person records gifts and envelopes in the gift register | Day-of |  | 2027-04-01 | To do | 150
On the day | Pay vendor balances after the service and take receipts | Day-of |  | 2027-04-01 | To do | 150
On the day | Keep water and snacks for the couple and elders | Day-of |  | 2027-04-01 | To do | 150
After the event | Count and deposit cash gifts; finish the gift register | Planning |  | 2027-04-15 | To do | 164
After the event | Send thank-you messages to guests | Guests |  | 2027-04-15 | To do | 164
After the event | Return rented outfits, jewellery and decor items | Attire & beauty |  | 2027-04-15 | To do | 164
After the event | Settle every vendor account and close the budget | Planning |  | 2027-04-15 | To do | 164
After the event | Register the marriage and collect the certificate | Paperwork |  | 2027-04-15 | To do | 164
After the event | Update names and addresses on IDs and bank accounts if needed | Paperwork |  | 2027-04-15 | To do | 164
After the event | Collect photos and video; leave reviews for good vendors | Venue & vendors |  | 2027-04-15 | To do | 164
Formulas:
Due date = IF([When]="","",Settings!$B4+IFERROR(VLOOKUP([When],Settings!$D3:E13,2,FALSE),0))
Days left = IF(OR([Due date]="",[Status]="Done",[Status]="Not needed"),"",[Due date]-TODAY())
Overdue = IF(AND([Due date]<>"",[Status]<>"Done",[Status]<>"Not needed",N([Due date])<TODAY()),"Overdue","")

## Progress
Progress
Tasks marked Not needed are left out.
Period | Tasks | Done | Open | Overdue | % done
12+ months before | 7 | 4 | 3 | 3 | 57.14%
9-12 months before | 6 | 0 | 6 | 6 | 0%
6-9 months before | 8 | 0 | 8 | 8 | 0%
4-6 months before | 7 | 0 | 7 | 0 | 0%
2-3 months before | 8 | 0 | 8 | 0 | 0%
1 month before | 6 | 0 | 6 | 0 | 0%
2 weeks before | 6 | 0 | 6 | 0 | 0%
Last week | 6 | 0 | 6 | 0 | 0%
Day before | 4 | 0 | 4 | 0 | 0%
On the day | 5 | 0 | 5 | 0 | 0%
After the event | 7 | 0 | 7 | 0 | 0%
All tasks | 70 | 4 | 66 | 17 | 5.714%
Days to go: 150

## Lists (hidden)
₹ | Indian (12,34,567) | 31-12-2026 | Yes | 12+ months before | Planning | To do
$ | International (1,234,567) | 31-Dec-2026 | No | 9-12 months before | Venue & vendors | In progress
€ |  | 12/31/2026 |  | 6-9 months before | Guests | Done
£ |  | 2026-12-31 |  | 4-6 months before | Attire & beauty | Not needed
AED |  |  |  | 2-3 months before | Rituals
SAR |  |  |  | 1 month before | Paperwork
QAR |  |  |  | 2 weeks before | Travel & stay
KWD |  |  |  | Last week | Day-of
OMR |  |  |  | Day before
BHD |  |  |  | On the day
SGD |  |  |  | After the event
MYR
A$
C$
NZ$
NPR
PKR
BDT
LKR
ZAR
KES
NGN
Rs