## How to use
Gantt Chart Project Plan (Excel)
Toolkit by GroupChatOn · free template · https://toolkit.groupchaton.com
Type each task's start date and how many working days it takes; the workbook works out the end date (skipping your weekly offs and holidays), draws the bar across a weekly or daily timeline, shades the part already done and marks today with a red column. Late tasks turn red by themselves, so the plan tells you where to look without anyone colouring cells by hand.
Colours
Yellow cells: type or pick here.
Grey and white cells: calculate by themselves. Don't type over them.
Steps
1 | Open the Settings sheet. Type the project name and manager, and pick your weekly off days from the list.
2 | Add your public holidays and office closures on the Holidays sheet, one date per row.
3 | On the Plan sheet, delete the sample rows: select the yellow cells from row 6 down and press Delete.
4 | Add a Phase row for each stage of the project (for example Plan, Design, Build, Launch) and the tasks under it. Pick "Milestone" for a checkpoint such as "Design approved" and give it a duration of 0.
5 | For each task type the start date and the duration in working days. The end date, the bar and the status fill in by themselves.
6 | Each week, update the % done of every task that moved. The darker part of the bar grows and the Summary sheet shows the overall progress.
7 | To see a long project, set the scale to Weeks; to plan a short one in detail, set it to Days and the timeline start a few days before the first task.
Tips
• | Keep tasks between 2 and 15 working days. Longer tasks hide problems; shorter ones turn the plan into a to-do list.
• | Write tasks as outcomes ("Home page design approved") rather than activities ("Work on design") so it is clear when they are done.
• | When a date slips, change the start or duration instead of colouring cells: the bars, status and summary follow.
• | Use the "Depends on" column to note which task must finish first, then check those pairs whenever a date changes.
• | Freeze the first columns (already done) and print with File › Print › Landscape; the sheet is set to fit one page wide.
Full guide, questions and answers, and more free templates:
https://toolkit.groupchaton.com/projects/pm-gantt-chart-excel/
Designed & Developed by: Nivesh Sahayak
Free to use for your own work and your clients' work. Please don't sell or re-publish this file. The calculations are a help, not professional advice: check figures, tax rates and rules before you rely on them.

## Settings
Project settings
Yellow cells: type or pick. The Plan and Summary sheets use these.
Project name | Company website redesign
Project manager | Priya Nair
Weekly off days | Saturday and Sunday | End dates skip these days and every date on the Holidays sheet.
Timeline starts on | 2026-10-12 | Starts on the Monday before the first task. Type any date to move the chart (for example to see later months).
Timeline scale | Weeks | Weeks: each timeline column is 7 days (30 weeks shown). Days: each column is one day (30 days shown).
Weekend code (used by formulas) | 0000011
Days per timeline column | 7

## Plan
Project plan and Gantt chart
Yellow: type. Grey: works itself out. Phase rows: leave Start, Duration and % done empty; they come from the tasks below.
Project: Company website redesign · Manager: Priya Nair · Weekly off: Saturday and Sunday | [39 empty] | 7 | 0000011
[10 empty] | Oct |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May
ID | Task, milestone or phase | Type | Owner | Start | Duration (work days) | End | % done | Status | Depends on | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | Bar start | Bar end | Done share | Rows in phase | Open milestone
1 | Plan | Phase |  |  |  | 2026-10-20 |  | Done | [31 empty] | 46307 | 46315 | 1 | 3
1.1 | Project kick-off held | Milestone | Priya | 2026-10-12 | 0 | 2026-10-12 | 100% | Done | [31 empty] | 46307 | 46307 | 1 | 0 | bar: 2026-10-12
1.2 | Requirements and sitemap agreed | Task | Priya | 2026-10-12 | 5 | 2026-10-16 | 100% | Done | 1.1 | [30 empty] | 46307 | 46311 | 1 | 0
1.3 | Content inventory of the old site | Task | Sana | 2026-10-15 | 4 | 2026-10-20 | 100% | Done | [31 empty] | 46310 | 46315 | 1 | 0
2 | Design | Phase |  |  |  | 2026-11-03 |  | In progress | [31 empty] | 46314 | 46329 | 0.92308 | 3
2.1 | Home page and key page mockups | Task | Arjun | 2026-10-19 | 8 | 2026-10-28 | 100% | Done | 1.2 | [30 empty] | 46314 | 46323 | 1 | 0
2.2 | Mobile layouts and style guide | Task | Arjun | 2026-10-26 | 5 | 2026-10-30 | 80% | Late | 2.1 | [30 empty] | 46321 | 46325 | 0.8 | 0
2.3 | Design approved by sponsor | Milestone | Priya | 2026-11-03 | 0 | 2026-11-03 | 0% | Not started | 2.2 | [30 empty] | 46329 | 46329 | 0 | 0 | 46329 | bar: 2026-11-02
3 | Build | Phase |  |  |  | 2026-11-20 |  | In progress | [31 empty] | 46317 | 46346 | 0.26897 | 4
3.1 | Hosting and staging site set up | Task | Vikram | 2026-10-22 | 3 | 2026-10-26 | 100% | Done | [31 empty] | 46317 | 46321 | 1 | 0
3.2 | Page templates built | Task | Vikram | 2026-11-03 | 10 | 2026-11-16 | 0% | Not started | 2.3 | [30 empty] | 46329 | 46342 | 0 | 0
3.3 | Page content written and edited | Task | Sana | 2026-10-28 | 12 | 2026-11-12 | 40% | In progress | 1.3 | [30 empty] | 46323 | 46338 | 0.4 | 0
3.4 | Contact form and analytics working | Task | Vikram | 2026-11-17 | 4 | 2026-11-20 | 0% | Not started | 3.2 | [30 empty] | 46343 | 46346 | 0 | 0
4 | Test and launch | Phase |  |  |  | 2026-12-10 |  | Not started | [31 empty] | 46349 | 46366 | 0 | 136
4.1 | Tested on phones and browsers | Task | Meera | 2026-11-23 | 5 | 2026-11-27 | 0% | Not started | 3.4 | [30 empty] | 46349 | 46353 | 0 | 0
4.2 | Defects fixed, final review | Task | Vikram | 2026-11-30 | 4 | 2026-12-03 | 0% | Not started | 4.1 | [30 empty] | 46356 | 46359 | 0 | 0
4.3 | Staff trained to edit pages | Task | Sana | 2026-12-01 | 2 | 2026-12-02 | 0% | Not started | [31 empty] | 46357 | 46358 | 0 | 0
4.4 | Website live | Milestone | Priya | 2026-12-07 | 0 | 2026-12-07 | 0% | Not started | 4.2 | [30 empty] | 46363 | 46363 | 0 | 0 | 46363 | bar: 2026-12-07
4.5 | Post-launch check and handover | Task | Priya | 2026-12-08 | 3 | 2026-12-10 | 0% | Not started | 4.4 | [30 empty] | 46364 | 46366 | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0
[42 empty] | 0 | 0

## Holidays
Holidays and office closures
One date per row. End dates on the Plan skip these days.
Date | Holiday
2026-12-25 | Christmas Day
2027-01-01 | New Year's Day
2027-01-26 | Republic Day (India): replace with your own holidays

## Summary
Project summary
Everything here works itself out from the Plan sheet.
Project | Company website redesign | Tasks by status | Count
Project manager | Priya Nair | Done | 4
Planned start | 2026-10-12 | In progress | 1
Planned finish | 2026-12-10 | Late | 1
Working days in the plan | 44 | Not started | 6
Time gone (calendar) | 36.67% | Not planned | 0
Work done (weighted by duration) | 44.31% | All tasks | 12
Next open milestone | Design approved by sponsor | Milestones done | 1 of 3
Milestone date | 2026-11-03
When work done is well behind time gone, the project is probably late even if no single task shows Late yet.

## Lists (hidden)
Saturday and Sunday | 0000011 | Phase | Weeks
Sunday only | 0000001 | Task | Days
Friday and Saturday | 0000110 | Milestone
Friday only | 0000100
No weekly off | 0000000