## How to use
Project Budget vs Actual (Excel)
Toolkit by GroupChatOn · free template · https://toolkit.groupchaton.com
Plan the project budget line by line, then log every bill and purchase order as it comes in. The workbook adds them up per line into committed (ordered, not yet paid) and actual (paid), takes your estimate of what is still to come, forecasts the final cost and shows the variance against budget in amount and percent. Lines heading over budget turn amber and red long before the money runs out.
Colours
Yellow cells: type or pick here.
Grey and white cells: calculate by themselves. Don't type over them.
Steps
1 | On the Settings sheet type the project name, your currency and the start month.
2 | On the Budget sheet replace the sample work packages with your own. Give each a cost type and a budget amount.
3 | Log each purchase order or bill on the Spending sheet. Pick the budget line, type the amount and choose "Committed" for an order not yet paid or "Paid" once it is paid.
4 | When an order is paid, change its status from Committed to Paid. Do not add a second row.
5 | Once a month, update the "Estimate to complete" column on the Budget sheet: how much more each line will still cost.
6 | Read the status: green OK, amber Watch (90% or more of the line is already committed or paid, or your estimate puts the forecast within 5% of the budget), red Over budget. Report the forecast at completion, not just the money spent.
Tips
• | Committed costs matter: an order already placed is money you can no longer spend elsewhere.
• | If the estimate to complete is left empty, the forecast assumes the remaining budget will be spent exactly, which is optimistic. Fill it in.
• | Keep contingency as its own budget line and log its use with a note of which risk or change it paid for.
• | For tax, accounting or contract questions about project costs, check with your accountant or finance team.
Full guide, questions and answers, and more free templates:
https://toolkit.groupchaton.com/projects/pm-budget-vs-actual-excel/
Designed & Developed by: Nivesh Sahayak
Free to use for your own work and your clients' work. Please don't sell or re-publish this file. The calculations are a help, not professional advice: check figures, tax rates and rules before you rely on them.

## Settings
Settings
Type once. Every heading shows your currency.
Project name | Company website redesign | Cost types
Currency (code or symbol) | USD | Labour
First month of the project | 2026-10-01 | Materials
Equipment
Approved budget (total of lines) | 19250 | Software and licences
Forecast at completion | 19370 | Services and contractors
Variance (+ saving, − overspend) | -120 | Travel
Training
Change or add cost types in the yellow list on the right. Keep "Contingency" for the reserve so its use is visible. |  | Contingency
Other

## Budget
Budget vs actual by line
Yellow: type. Committed and actual come from the Spending sheet.
Project: Company website redesign · Currency: USD
Budget line / work package | Cost type | Budget (USD) | Committed (USD) | Actual (paid) (USD) | Remaining (USD) | Estimate to complete (USD) | Forecast at completion (USD) | Variance (USD) | Variance % | Status
Project manager (part time) | Labour | 4000 | 0 | 2000 | 2000 |  | 4000 | 0 | 0% | OK
Web developer | Labour | 6500 | 0 | 1600 | 4900 | 4800 | 6400 | 100 | 1.538% | Watch
Design agency | Services and contractors | 3000 | 1700 | 1500 | -200 | 0 | 3200 | -200 | -6.667% | Over budget
Content writing and translation | Services and contractors | 1500 | 0 | 0 | 1500 |  | 1500 | 0 | 0% | OK
Hosting and domain (first year) | Software and licences | 600 | 0 | 540 | 60 |  | 600 | 0 | 0% | Watch
Website builder and plugins | Software and licences | 450 | 0 | 470 | -20 |  | 470 | -20 | -4.444% | Over budget
Photography | Services and contractors | 800 | 800 | 0 | 0 |  | 800 | 0 | 0% | Watch
Testing devices | Equipment | 350 | 0 | 0 | 350 |  | 350 | 0 | 0% | OK
Staff training | Training | 300 | 0 | 0 | 300 |  | 300 | 0 | 0% | OK
Contingency (10%) | Contingency | 1750 | 400 | 0 | 1350 |  | 1750 | 0 | 0% | OK
Total |  | 19250 | 2900 | 6110 | 10240 | 4800 | 19370 | -120 | -0.6234% | Over budget

## Spending
Spending log
One row per purchase order or bill. Change Committed to Paid when you pay it; do not add a second row.
Date | Budget line | Description | Supplier / person | Reference | Amount (USD) | Status | Month
2026-10-05 | Project manager (part time) | PM time, month 1 | Priya Nair | TS-01 | 1000 | Paid | 2026-10-01
2026-10-08 | Hosting and domain (first year) | Hosting plan, 12 months | HostCo | INV-5521 | 540 | Paid | 2026-10-01
2026-10-12 | Design agency | Design: 50% advance | Pixel Studio | PO-104 | 1500 | Paid | 2026-10-01
2026-10-12 | Design agency | Design: balance on approval | Pixel Studio | PO-104 | 1700 | Committed | 2026-10-01
2026-10-20 | Web developer | Development, sprint 1 | Vikram Rao | INV-031 | 1600 | Paid | 2026-10-01
2026-11-03 | Website builder and plugins | Theme and form plugin licences | WebKit Ltd | INV-889 | 470 | Paid | 2026-11-01
2026-11-05 | Project manager (part time) | PM time, month 2 | Priya Nair | TS-02 | 1000 | Paid | 2026-11-01
2026-11-10 | Photography | Office and team photo shoot | Lens & Light | PO-107 | 800 | Committed | 2026-11-01
2026-11-18 | Contingency (10%) | Extra design round (risk R-06) | Pixel Studio | PO-110 | 400 | Committed | 2026-11-01

## Monthly
Spending by month
Money paid each month and the running total against the budget.
Month | Paid (USD) | Committed (ordered) (USD) | Paid to date (USD) | % of budget
2026-10-01 | 4640 | 1700 | 4640 | 24.1%
2026-11-01 | 1470 | 1200 | 6110 | 31.74%
2026-12-01 | 0 | 0 | 6110 | 31.74%
2027-01-01 | 0 | 0 | 6110 | 31.74%
2027-02-01 | 0 | 0 | 6110 | 31.74%
2027-03-01 | 0 | 0 | 6110 | 31.74%
2027-04-01 | 0 | 0 | 6110 | 31.74%
2027-05-01 | 0 | 0 | 6110 | 31.74%
2027-06-01 | 0 | 0 | 6110 | 31.74%
2027-07-01 | 0 | 0 | 6110 | 31.74%
2027-08-01 | 0 | 0 | 6110 | 31.74%
2027-09-01 | 0 | 0 | 6110 | 31.74%
2027-10-01 | 0 | 0 | 6110 | 31.74%
2027-11-01 | 0 | 0 | 6110 | 31.74%
2027-12-01 | 0 | 0 | 6110 | 31.74%
2028-01-01 | 0 | 0 | 6110 | 31.74%
2028-02-01 | 0 | 0 | 6110 | 31.74%
2028-03-01 | 0 | 0 | 6110 | 31.74%

## Summary
Summary by cost type
Budget, spending and forecast per type of cost.
Cost type | Budget (USD) | Committed (USD) | Actual (paid) (USD) | Forecast (USD) | Variance (USD) | Status
Labour | 10500 | 0 | 3600 | 10400 | 100 | OK
Materials | 0 | 0 | 0 | 0 | 0
Equipment | 350 | 0 | 0 | 350 | 0 | OK
Software and licences | 1050 | 0 | 1010 | 1070 | -20 | Over
Services and contractors | 5300 | 2500 | 1500 | 5500 | -200 | Over
Travel | 0 | 0 | 0 | 0 | 0
Training | 300 | 0 | 0 | 300 | 0 | OK
Contingency | 1750 | 400 | 0 | 1750 | 0 | OK
Other | 0 | 0 | 0 | 0 | 0
Total | 19250 | 2900 | 6110 | 19370 | -120
Contingency used | 22.86% | Share of the contingency line already committed or paid.