## How to use
RACI Matrix (Excel)
Toolkit by GroupChatOn · free template · https://toolkit.groupchaton.com
A RACI matrix answers "who does what" before it becomes an argument. List the project's deliverables and decisions down the side and the people or roles across the top, then mark each cell R, A, C or I. The workbook colours the letters, checks every row has exactly one Accountable person and at least one Responsible, and counts each person's load so you can see who is overloaded and who is only being told.
Colours
Yellow cells: type or pick here.
Grey and white cells: calculate by themselves. Don't type over them.
Steps
1 | Type the roles or people across row 5 (for example Sponsor, Project manager, Designer, Developer, Finance, Client).
2 | List the activities, deliverables and decisions down column B, grouped by phase in column A.
3 | For each row pick a letter under each role who is involved. Leave the cell empty for people who are not.
4 | Fix every row whose Check column is not "OK": give it exactly one A and at least one R.
5 | Look at the load table under the matrix. Spread the work if one person has most of the Rs or As.
6 | Share the sheet at the kick-off meeting and ask everyone to confirm their letters.
Tips
• | Only one person can be Accountable for a row. If two people "own" it, it is really two rows or one of them is Consulted.
• | Keep Consulted short: each C is a person whose opinion you must wait for.
• | Use roles rather than names when people may change during the project, and keep a names list in the charter.
• | Revisit the matrix when someone joins or leaves the team.
Full guide, questions and answers, and more free templates:
https://toolkit.groupchaton.com/projects/pm-raci-matrix-excel/
Designed & Developed by: Nivesh Sahayak
Free to use for your own work and your clients' work. Please don't sell or re-publish this file. The calculations are a help, not professional advice: check figures, tax rates and rules before you rely on them.

## RACI
RACI matrix
Type the roles in the yellow cells of row 5, then pick R, A, C, I or A/R in each cell. One A per row.
R = Responsible (does the work) · A = Accountable (owns it, one per row) · C = Consulted (asked before) · I = Informed (told after)
Phase | Activity, deliverable or decision | Sponsor | Project manager | Product owner | Designer | Developer | Content writer | QA tester | Marketing | IT support | Finance | Check
Start | Project charter approved | A | R | C |  |  |  |  | I |  | C | OK
Start | Budget approved | A | R | [7 empty] | C | OK
Start | Requirements and sitemap | I | A | R | C | C | C |  | C |  |  | OK
Design | Page mockups | I | C | A | R | C | C |  | C |  |  | OK
Design | Design sign-off | A | R | C | C | I |  |  | I |  |  | OK
Build | Hosting and domain set-up |  | C |  |  | R |  |  |  | A | I | OK
Build | Page templates |  | C | A | C | R |  | I |  |  |  | OK
Build | Page content |  | C | A |  |  | R |  | C |  |  | OK
Build | Choose hosting provider | A | A |  |  | R |  |  |  | C | C | More than one A
Test | Testing on phones and browsers |  | I | C | C | C |  | A/R |  |  |  | OK
Launch | Go-live decision | A | R | C |  | C |  | C | I | I |  | OK
Launch | Staff training |  | A | C |  | C | R |  |  | I |  | OK
Launch | Launch announcement | I | C | C | C |  | C |  | A/R |  |  | OK
Close | Handover to support | I | A |  |  | R |  |  |  | R |  | OK
Close | Final cost report | I | A | [7 empty] | R | OK
Close | Lessons learned meeting | C | A/R | C | C | C | C | C | C | C | I | OK
Load per role
Role |  | R | A | C | I | Total | Share of all A | Note
Sponsor |  | 0 | 5 | 1 | 5 | 11 | 29.41%
Project manager |  | 5 | 6 | 5 | 1 | 16 | 35.29%
Product owner |  | 1 | 3 | 7 | 0 | 11 | 17.65%
Designer |  | 1 | 0 | 6 | 0 | 7 | 0%
Developer |  | 4 | 0 | 6 | 1 | 11 | 0%
Content writer |  | 2 | 0 | 4 | 0 | 6 | 0%
QA tester |  | 1 | 1 | 2 | 1 | 4 | 5.882%
Marketing |  | 1 | 1 | 4 | 3 | 8 | 5.882%
IT support |  | 1 | 1 | 2 | 2 | 6 | 5.882%
Finance |  | 1 | 0 | 3 | 2 | 6 | 0%

## Guide
How RACI works
Share this sheet with the team at the kick-off meeting.
Letter | Meaning
R | Responsible: does the work. At least one per row; several people can share it.
A | Accountable: owns the result, approves it and answers for it. Exactly one person per row.
C | Consulted: asked for input before the work is done or the decision is made. Two-way conversation.
I | Informed: told about progress or the decision after it happens. One-way.
A/R | The same person both does the work and owns it. Common for small tasks.
Rules the Check column applies
• Every row needs exactly one A. "No A" means nobody owns the result; "More than one A" means nobody really does.
• Every row needs at least one R, otherwise nobody does the work.
• An activity with no letters at all shows "Not assigned".
Good practice
• Push accountability down to the person closest to the work, not always to the manager.
• Too many Cs slow the project: every C is someone you must wait for.
• A role with only Is may not need to be in the project team; keep them on the report list instead.
• Go through the matrix with every person named in it and agree it, then keep it with the project charter.