## How to use
Risk, Issue & Change Log (Excel)
Toolkit by GroupChatOn · free template · https://toolkit.groupchaton.com
Three registers every project needs, in one workbook. Risks are things that might happen: each gets a probability and impact from 1 to 5, a score and a heat colour, a response and an owner, and appears on a 5×5 heat map. Issues are things that have already happened: each has a priority, an owner, a target date and a days-open counter. Change requests record what was asked to change, its effect on cost and time, and who approved it.
Colours
Yellow cells: type or pick here.
Grey and white cells: calculate by themselves. Don't type over them.
Steps
1 | On the Settings sheet type your currency (for example USD, €, ₹ or AED). Change the rating limits only if your organisation uses different ones.
2 | Delete the sample rows on the Risks, Issues and Changes sheets.
3 | For each risk, write it as "Because of [cause], [event] may happen, which would [effect]". Pick its probability and impact from 1 (very low) to 5 (very high).
4 | Choose a response (Avoid, Reduce, Transfer or Accept), write the action, give it an owner and a due date.
5 | When a risk happens, set its status to "Became an issue" and add it to the Issues sheet.
6 | Log every change request as it arrives, fill in its cost and time impact, and record the decision once the sponsor or change board has decided.
7 | Review the Heat Map and the Dashboard in every weekly meeting.
Tips
• | A risk without an owner and a date is just a worry. Make sure every open risk has both.
• | Fill in the "after action" probability and impact to show how much the action is expected to reduce the risk.
• | Close a risk when the period it could happen in is over; keep it in the list with status Closed for the record.
• | Approved changes should update the plan and the budget: copy the cost into the budget workbook and move the dates in the Gantt chart.
Full guide, questions and answers, and more free templates:
https://toolkit.groupchaton.com/projects/pm-risk-issue-log-excel/
Designed & Developed by: Nivesh Sahayak
Free to use for your own work and your clients' work. Please don't sell or re-publish this file. The calculations are a help, not professional advice: check figures, tax rates and rules before you rely on them.

## Settings
Settings and lists
Yellow cells can be changed. The lists feed the drop-downs on the other sheets.
Currency (code or symbol) | USD | Risk categories | Risk status | Response | Issue status | Priority | CR decision | Change type
|  | Schedule | Open | Avoid | Open | High | Pending | Scope
Medium from score | 5 | Cost | Monitoring | Reduce | In progress | Medium | Approved | Schedule
High from score | 10 | Scope | Closed | Transfer | Resolved | Low | Rejected | Cost
Critical from score | 20 | Quality | Became an issue | Accept | Closed |  | Deferred | Quality
Score = probability × impact (1 to 25). Below the Medium limit a risk is Low. |  | People and skills |  | Exploit (opportunity) |  |  |  | Resources
|  | Technical | [5 empty] | Other
Supplier
Legal and compliance
Stakeholders
External

## Risks
Risk register
Write each risk as: because of [cause], [event] may happen, which would [effect].
ID | Raised on | Risk (cause → event → effect) | Category | Owner | Probability (1-5) | Impact (1-5) | Score | Rating | Response | Action to take | Action due | Status | Prob. after | Impact after | Score after | Last reviewed | Due check
R-01 | 2026-10-03 | Because the sponsor is travelling in the design phase, design approval may be delayed, which would push back the build. | Stakeholders | Priya | 3 | 4 | 12 | High | Reduce | Book two review slots now; agree a deputy who can approve. | 2026-11-07 | Open | 2 | 4 | 8 | 2026-10-30 |  | 12.0994
R-02 | 2026-10-05 | Because only one developer knows the hosting set-up, illness or leave may stop the build, which would delay go-live by weeks. | People and skills | Vikram | 2 | 5 | 10 | High | Reduce | Write a set-up note; pair a second developer for one day a week. | 2026-10-31 | Open | 2 | 3 | 6 | 2026-10-30 | Overdue | 10.0993
R-03 | 2026-10-08 | Because content comes from five departments, pages may arrive late or incomplete, which would delay testing. | Schedule | Sana | 4 | 3 | 12 | High | Reduce | Weekly content deadline per department; send a page template with word limits. | 2026-11-11 | Monitoring | 3 | 3 | 9 | 2026-10-30 |  | 12.0992
R-04 | 2026-10-13 | Because the hosting price is in a foreign currency, a currency change may raise the yearly cost, which would exceed the budget line. | Cost | Finance | 2 | 2 | 4 | Low | Accept | Keep 5% contingency on the hosting line. | 2026-12-02 | Open | 2 | 2 | 4 | 2026-10-30 |  | 4.0991
R-05 | 2026-10-15 | Because the old site has no redirects planned, search engines may drop old pages, which would lose enquiries after launch. | Technical | Vikram | 3 | 4 | 12 | High | Avoid | List every old address and map it to a new page before launch. | 2026-11-22 | Open | 1 | 4 | 4 | 2026-10-30 |  | 12.099
R-06 | 2026-10-19 | Because the design agency may be late, mockups may arrive after the review date, which would delay sign-off. | Supplier | Arjun | 3 | 3 | 9 | Medium | Transfer | Penalty clause for late delivery agreed in the purchase order. | 2026-10-23 | Became an issue |  |  |  | 2026-10-30
Formulas:
Due check = IF(OR([Action due]="",[Status]="Closed",[Status]="Became an issue"),"",IF([Action due]<TODAY(),"Overdue",""))

## Heat Map
Risk heat map | [6 empty] | 5
Number of Open and Monitoring risks at each probability and impact. | [6 empty] | 10
20
Impact →
Probability ↓ |  | 1 | 2 | 3 | 4 | 5
Almost certain | 5 | 0 | 0 | 0 | 0 | 0
Likely | 4 | 0 | 0 | 1 | 0 | 0
Possible | 3 | 0 | 0 | 0 | 2 | 0
Unlikely | 2 | 0 | 1 | 0 | 0 | 1
Rare | 1 | 0 | 0 | 0 | 0 | 0
|  | Minor | Small | Noticeable | Serious | Severe
Colours follow the score limits on the Settings sheet: green Low, yellow Medium, orange High, red Critical. Work on the top-right corner first.

## Issues
Issue log
Problems happening now. Every issue needs an owner, an action and a target date.
ID | Raised on | Issue | Priority | Owner | Action / resolution | Target date | Status | Resolved on | Days open | Due check | From risk
I-01 | 2026-10-23 | Design agency delivered mockups 6 days late; sign-off meeting moved. | High | Arjun | Agency working Saturday; new review date agreed with sponsor. | 2026-11-05 | In progress |  | 10 |  | R-06
I-02 | 2026-10-27 | Staging server password shared on chat. | Medium | Vikram | Password changed; access list reviewed. | 2026-10-29 | Resolved | 2026-10-28 | 1
I-03 | 2026-10-29 | Finance department has not sent its page content. | Medium | Sana | Escalate to finance manager at the weekly meeting. | 2026-11-01 | Open |  | 4 | Overdue | R-03
Formulas:
Days open = IF([Raised on]="","",IF([Resolved on]<>"",[Resolved on],TODAY())-[Raised on])
Due check = IF(AND([Target date]<>"",OR([Status]="Open",[Status]="In progress"),[Target date]<TODAY()),"Overdue","")

## Changes
Change request log
Every request to change scope, time, cost or quality, and what was decided.
CR no. | Raised on | Requested by | Change requested | Reason / benefit | Type | Cost impact (USD) | Days impact | Priority | Decision | Decided by | Decision date | Days waiting | Notes
CR-01 | 2026-10-13 | Marketing | Add a blog section with categories | Regular articles to bring search traffic | Scope | 1800 | 6 | Medium | Approved | Sponsor | 2026-10-18 | 5 | Templates in build task 3.2
CR-02 | 2026-10-21 | Sales | Online chat widget on every page | Faster replies to enquiries | Scope | 600 | 2 | Low | Deferred | Sponsor | 2026-10-24 | 3 | After launch, phase 2
CR-03 | 2026-10-28 | Sponsor | Hindi version of the five main pages | Customers in north India | Scope | 2400 | 8 | High | Pending |  |  | 5 | Translation quote awaited | 5

## Dashboard
Risks, issues and changes at a glance
Updates by itself from the three logs.
Open risks by rating |  | Count |  |  | Open issues | Count | Overdue
Critical |  | 0 |  |  | High | 1 | 0
High |  | 4 |  |  | Medium | 1 | 1
Medium |  | 0 |  |  | Low | 0 | 0
Low |  | 1
Risk actions overdue |  | 1
[5 empty] | Change requests | Count | Days
[5 empty] | Pending | 1 | 8
ID | Top open risks | Owner | Score | Rating | Approved | 1 | 6
R-01 | Because the sponsor is travelling in the design phase, design approval may be delayed, which would push back the build. | Priya | 12 | High | Rejected | 0 | 0
R-03 | Because content comes from five departments, pages may arrive late or incomplete, which would delay testing. | Sana | 12 | High | Deferred | 1 | 2
R-05 | Because the old site has no redirects planned, search engines may drop old pages, which would lose enquiries after launch. | Vikram | 12 | High
R-02 | Because only one developer knows the hosting set-up, illness or leave may stop the build, which would delay go-live by weeks. | Vikram | 10 | High | Cost of approved changes (USD) | 1800
R-04 | Because the hosting price is in a foreign currency, a currency change may raise the yearly cost, which would exceed the budget line. | Finance | 4 | Low | Oldest pending (days) | 5